## original_wbs
ID | Name | Successors | Duration | Work Content
0 | Dummy work package | 1,9,10,11 | 0 | 0
1 | Formwork samples making | 2,3
1.1 | Formwork design | 1.3 | 3d | 3p*d
1.2 | Determine the material | 1.3 | 1d | 1p*d
1.3 | Cavity making | 1.4 | 3d | 3p*d
1.4 | Formwork making | 1.5 | 7d | 7p*d
1.5 | Test | N/A | 1d | 1p*d
2 | Formworks batch production | 4
2.1 | First batch of formwork making | 2.2,2.3 | 7d | 7p*d
2.2 | First batch of formwork test | N/A | 1d | 1p*d
2.3 | Second batch of formwork making | 2.4,2.5 | 7d | 7p*d
2.4 | Second batch of formwork test | N/A | 1d | 1p*d
2.5 | Third batch of formwork making | 2.6 | 7d | 7p*d
2.6 | Third batch of formwork test | N/A | 1d | 1p*d
3 | Mock-up production | 4
3.1 | Mock-up production making | 4.2,4.3 | 5d | 5p*d
3.2 | Mock-up production decoration work | 4.4 | 18d | 18p*d
3.3 | Mock-up production test | 4.4 | 1d | 1p*d
3.4 | Mock-up production acceptance | N/A | 1d | 1p*d
4 | The first batch of MiC production | 5,7
4.1 | Production preparation | 4.2,4.3,4.4 | 2d | 2p*d
4.2 | Cleaning formwork | 4.5 | 1d | 1p*d
4.3 | Rebar binding | 4.5 | 1d | 1p*d
4.4 | Blanking | 4.7 | 1d | 1p*d
4.5 | Rebar cages installation | 4.6 | 3d | 3p*d
4.6 | Formwork installation | 4.7 | 2d | 2p*d
4.7 | Concrete pouring and curing | 4.8 | 12d | 12p*d
4.8 | Formwork demolition | 4.9,4.10 | 1d | 1p*d
4.9 | Wall and ceiling decorations | 4.11 | 3d | 3p*d
4.1 | Floor decorations | 4.12 | 1d | 1p*d
4.11 | Waterproofing | 4.13 | 1d | 1p*d
4.12 | Electromechanical installation | 4.13 | 1d | 1p*d
4.13 | Test | N/A | 1d | 1p*d
5 | The second batch of MiC production | 6,8
5.1 | Production preparation | 5.2,5.3,5.4 | 2d | 2p*d
5.2 | Cleaning formwork | 5.5 | 1d | 1p*d
5.3 | Rebar binding | 5.5 | 1d | 1p*d
5.4 | Blanking | 5.7 | 1d | 1p*d
5.5 | Rebar cages installation | 5.6 | 2d | 2p*d
5.6 | Formwork installation | 5.7 | 2d | 2p*d
5.7 | Concrete pouring and curing | 5.8 | 12d | 12p*d
5.8 | Formwork demolition | 5.9,5.10 | 1d | 1p*d
5.9 | Wall and ceiling decorations | 5.11 | 2d | 2p*d
5.1 | Floor decorations | 5.12 | 1d | 1p*d
5.11 | Waterproofing | 5.13 | 1d | 1p*d
5.12 | Electromechanical installation | 5.13 | 1d | 1p*d
5.13 | Test | N/A | 1d | 1p*d
6 | Other batches of MiC production | 26
6.1 | Production preparation | 6.2 | 3d | 3p*d
6.2 | Structural Engineering | 6.3,6.5 | 14d | 14p*d
6.3 | Fitting out works | 6.4 | 3d | 3p*d
6.4 | Test | N/A | 1d | 1p*d
6.5 | Structural Engineering | 6.6,6.8 | 18d | 18p*d
6.6 | Fitting out works | 6.7 | 3d | 3p*d
6.7 | Test | N/A | 1d | 1p*d
6.8 | Structural Engineering | 6.9,6.11 | 14d | 14p*d
6.9 | Fitting out works | 6.1 | 3d | 3p*d
6.1 | Test | N/A | 1d | 1p*d
6.11 | Structural Engineering | 6.12 | 14d | 14p*d
6.12 | Fitting out works | 6.13 | 3d | 3p*d
6.13 | Test | N/A | 1d | 1p*d
7 | A small number of MICs are transported to the site | 8
7.1 | Preparation of personnel and tools | 7.4 | 1d | 1p*d
7.2 | Route planning | 7.4 | 1d | 1p*d
7.3 | Site and personnel preparation | 7.8 | 1d | 1p*d
7.4 | Precast units inspection | 7.5 | 1d | 1p*d
7.5 | Support and anti-skid device installation | 7.6 | 1d | 1p*d
7.6 | Precast units loading and inspection | 7.7 | 2d | 2p*d
7.7 | Precast units transportation | 7.8 | 1d | 1p*d
7.8 | Precast units entry and inspection | N/A | 1d | 1p*d
8 | Other MICs are transported into the site | 26
8.1 | Transportation preparation | 8.2,8.4 | 2d | 2p*d
8.2 | Transportation | 8.3,8.5 | 1d | 1p*d
8.3 | Precast units entry and inspection | 8.6 | 1d | 1p*d
8.4 | Transportation preparation | 8.5,8.7 | 2d | 2p*d
8.5 | Transportation | 8.6,8.8 | 1d | 1p*d
8.6 | Precast units entry and inspection | 8.9 | 1d | 1p*d
8.7 | Transportation preparation | 8.8,8.10 | 2d | 2p*d
8.8 | Transportation | 8.9,8.11 | 1d | 1p*d
8.9 | Precast units entry and inspection | 8.12 | 1d | 1p*d
8.1 | Transportation preparation | 8.11,8.13 | 2d | 2p*d
8.11 | Transportation | 8.12,8.14 | 1d | 1p*d
8.12 | Precast units entry and inspection | 8.15 | 1d | 1p*d
8.13 | Transportation preparation | 8.14,8.16 | 2d | 2p*d
8.14 | Transportation | 8.15,8.17 | 1d | 1p*d
8.15 | Precast units entry and inspection | 8.18 | 1d | 1p*d
8.16 | Transportation preparation | 8.17,8.19 | 2d | 2p*d
8.17 | Transportation | 8.18,8.20 | 1d | 1p*d
8.18 | Precast units entry and inspection | 8.21 | 1d | 1p*d
8.19 | Transportation preparation | 8.20,8.22 | 2d | 2p*d
8.2 | Transportation | 8.21,8.23 | 1d | 1p*d
8.21 | Precast units entry and inspection | 8.24 | 1d | 1p*d
8.22 | Transportation preparation | 8.23,8.25 | 2d | 2p*d
8.23 | Transportation | 8.24,8.26 | 1d | 1p*d
8.24 | Precast units entry and inspection | 8.27 | 1d | 1p*d
8.25 | Transportation preparation | 8.26,8.28 | 2d | 2p*d
8.26 | Transportation | 8.27,8.29 | 1d | 1p*d
8.27 | Precast units entry and inspection | 8.3 | 1d | 1p*d
8.28 | Transportation preparation | 8.29,8.31 | 2d | 2p*d
8.29 | Transportation | 8.30,8.32 | 1d | 1p*d
8.3 | Precast units entry and inspection | 8.33 | 1d | 1p*d
8.31 | Transportation preparation | 8.32,8.34 | 2d | 2p*d
8.32 | Transportation | 8.33,8.35 | 1d | 1p*d
8.33 | Precast units entry and inspection | 8.36 | 1d | 1p*d
8.34 | Transportation preparation | 8.35,8.37 | 2d | 2p*d
8.35 | Transportation | 8.36,8.38 | 1d | 1p*d
8.36 | Precast units entry and inspection | 8.39 | 1d | 1p*d
8.37 | Transportation preparation | 8.38,8.40 | 2d | 2p*d
8.38 | Transportation | 8.39,8.41 | 1d | 1p*d
8.39 | Precast units entry and inspection | 8.42 | 1d | 1p*d
8.4 | Transportation preparation | 8.41,8.43 | 2d | 2p*d
8.41 | Transportation | 8.42,8.44 | 1d | 1p*d
8.42 | Precast units entry and inspection | 8.45 | 1d | 1p*d
8.43 | Transportation preparation | 8.44,8.46 | 2d | 2p*d
8.44 | Transportation | 8.45,8.47 | 1d | 1p*d
8.45 | Precast units entry and inspection | 8.48 | 1d | 1p*d
8.46 | Transportation preparation | 8.47,8.49 | 2d | 2p*d
8.47 | Transportation | 8.48,8.50 | 1d | 1p*d
8.48 | Precast units entry and inspection | 8.51 | 1d | 1p*d
8.49 | Transportation preparation | 8.50,8.52 | 2d | 2p*d
8.5 | Transportation | 8.51,8.53 | 1d | 1p*d
8.51 | Precast units entry and inspection | 8.54 | 1d | 1p*d
8.52 | Transportation preparation | 8.53,8.55 | 2d | 2p*d
8.53 | Transportation | 8.54,8.56 | 1d | 1p*d
8.54 | Precast units entry and inspection | 8.57 | 1d | 1p*d
8.55 | Transportation preparation | 8.56,8.58 | 2d | 2p*d
8.56 | Transportation | 8.57,8.59 | 1d | 1p*d
8.57 | Precast units entry and inspection | 8.6 | 1d | 1p*d
8.58 | Transportation preparation | 8.59 | 2d | 2p*d
8.59 | Transportation | 8.6 | 1d | 1p*d
8.6 | Precast units entry and inspection | N/A | 1d | 1p*d
9 | 1,2# Building foundation construction | 12 | 27d() | 27p*d()
9.1 | Construction preparation | 9.2,9.6 | 1d | 1p*d
9.2 | 1# Building earthworks excavation | 9.3,9.4 | 10d | 10p*d
9.3 | 1# Building soil nail wall in outside | 9.5 | 3d | 3p*d
9.4 | 1# Building pile foundation | 9.5 | 12d | 12p*d
9.5 | 1# Building inspection | N/A | 1d | 1p*d
9.6 | 2# Building earthworks excavation | 9.7,9.8 | 10d | 10p*d
9.7 | 2# Building soil nail wall in outside | 9.9 | 3d | 3p*d
9.8 | 2# Building pile foundation | 9.9 | 12d | 12p*d
9.9 | 2# Building inspection | N/A | 1d | 1p*d
10 | 3,4,5# Building foundation construction | 13
10.1 | Construction preparation | 10.2,10.8,10.19 | 1d | 1p*d
10.2 | 3# Building soldier piles | 10.3 | 10d | 10p*d
10.3 | 3# Building jet grouting piles | 10.4 | 5d | 5p*d
10.4 | 3# Building bent cap construction | 10.5 | 4d | 4p*d
10.5 | 3# Building earthworks excavation | 10.6 | 14d | 14p*d
10.6 | 3# Building pile foundation | 10.7 | 28d | 28p*d
10.7 | 3# Building inspection | N/A | 1d | 1p*d
10.8 | 4# Building soldier piles | 10.9 | 14d | 14p*d
10.9 | 4# Building jet grouting piles | 10.1 | 6d | 6p*d
10.1 | 4# Building bent cap construction | 10.11 | 5d | 5p*d
10.11 | 4# Surface earthworks excavation | 10.12 | 1d | 1p*d
10.12 | 4# Building the first anchor cable construction | 10.13 | 18d | 18p*d
10.13 | 4# Building second earthworks excavation | 10.14,10.15,10.16 | 1d | 1p*d
10.14 | 4# Building second anchor cable construction | 10.17 | 18d | 18p*d
10.15 | 4# Building internal support beam construction | 10.17 | 6d | 6p*d
10.16 | 4# Building pile foundation | 10.18 | 18d | 18p*d
10.17 | 4# Building third earthworks excavation | 10.18 | 1d | 1p*d
10.18 | 4# Building inspection | N/A | 1d | 1p*d
10.19 | 5# Building soldier piles | 10.2 | 14d | 14p*d
10.2 | 5# Building jet grouting piles | 10.21 | 6d | 6p*d
10.21 | 5# Building bent cap construction | 10.22 | 5d | 5p*d
10.22 | 5# Surface earthworks excavation | 10.23 | 1d | 1p*d
10.23 | 5# Building the first anchor cable construction | 10.24 | 18d | 18p*d
10.24 | 5# Building second earthworks excavation | 10.25,10.26,10.27 | 1d | 1p*d
10.25 | 5# Building second anchor cable construction | 10.28 | 18d | 18p*d
10.26 | 5# Building internal support beam construction | 10.28 | 6d | 6p*d
10.27 | 5# Building pile foundation | 10.29 | 18d | 18p*d
10.28 | 5# Building third earthworks excavation | 10.29 | 1d | 1p*d
10.29 | 5# Building inspection | N/A | 1d | 1p*d
11 | Foundation construction in non-tower areas | 14
11.1 | Construction preparation | 11.2 | 1d | 1p*d
11.2 | Soldier piles | 11.3 | 12d | 12p*d
11.3 | Jet grouting piles | 11.4 | 12d | 12p*d
11.4 | Bent cap construction | 11.5 | 5d | 5p*d
11.5 | Earthworks excavation | 11.6 | 2d | 2p*d
11.6 | Pile foundation | 11.7 | 12d | 12p*d
11.7 | Inspection | N/A | 1d | 1p*d
12 | 1,2# Underground structure construction | 15
12.1 | Construction preparation | 12.2,12.6 | 1d | 1p*d
12.2 | 1# Building floor board | 12.3 | 18d | 18p*d
12.3 | 1# Building underground third-floor structure | 12.4 | 10d | 10p*d
12.4 | 1# Building underground second-floor structure | 12.5 | 7d | 7p*d
12.5 | 1# Building underground the first-floor structure | 12.1 | 10d | 10p*d
12.6 | 2# Building floor board | 12.7 | 18d | 18p*d
12.7 | 2# Building underground third-floor structure | 12.8 | 10d | 10p*d
12.8 | 2# Building underground second-floor structure | 12.9 | 7d | 7p*d
12.9 | 2# Building underground the first-floor structure | 12.1 | 10d | 10p*d
12.1 | Inspection | N/A | 1d | 1p*d
13 | 3,4,5# Underground structure construction | 16
13.1 | Construction preparation | 13.2,13.6 | 1d | 1p*d
13.2 | 3# Building floor board | 13.3 | 18d | 18p*d
13.3 | 3# Building underground third-floor structure | 13.4 | 10d | 10p*d
13.4 | 3# Building underground second-floor structure | 13.5 | 7d | 7p*d
13.5 | 3# Building underground the first-floor structure | 13.9 | 10d | 10p*d
13.6 | 4,5# Building floor board | 13.7 | 25d | 25p*d
13.7 | 4,5# Building underground second-floor structure | 13.8 | 10d | 10p*d
13.8 | 4,5# Building underground the first-floor structure | 13.9 | 10d | 10p*d
13.9 | Inspection | N/A | 1d | 1p*d
14 | Underground structure construction in non-tower areas | 17
14.1 | Construction preparation | 14.2 | 1d | 1p*d
14.2 | Building floor board | 14.3 | 18d | 18p*d
14.3 | Building underground third-floor structure | 14.4 | 12d | 12p*d
14.4 | Building underground second-floor structure | 14.5 | 12d | 12p*d
14.5 | Building underground the first-floor structure | 14.6 | 12d | 12p*d
14.6 | Capping and inspection | N/A | 2d | 2p*d
15 | 1,2# Building superstructure construction | 18,19,23
15.1 | Construction preparation | 15.2,15.6 | 1d | 1p*d
15.2 | 1# Building the first elevated floor | 15.3 | 7d | 7p*d
15.3 | 1# Building construction of structures from the second floor to the twenty-eighth floor | 15.4 | 100d | 100p*d
15.4 | 1# Building roof structure construction | 15.5 | 7d | 7p*d
15.5 | 1# Building main structure capping | 15.1 | 1d | 1p*d
15.6 | 2# Building the first elevated floor | 15.7 | 7d | 7p*d
15.7 | 2# Building construction of structures from the second floor to the twenty-eighth floor | 15.8 | 100d | 100p*d
15.8 | 2# Building roof structure construction | 15.9 | 7d | 7p*d
15.9 | 2# Building main structure capping | 15.1 | 1d | 1p*d
15.1 | Inspection and acceptance | N/A | 1d | 1p*d
16 | 3,4,5# Building superstructure construction | 20,21,22,24
16.1 | Construction preparation | 16.2,16.6 | 1d | 1p*d
16.2 | 3# Building the first elevated floor | 16.3 | 7d | 7p*d
16.3 | 3# Building construction of structures from the second floor to the twenty-eighth floor | 16.4 | 100d | 100p*d
16.4 | 3# Building roof structure construction | 16.5 | 7d | 7p*d
16.5 | 3# Building main structure capping | 16.1 | 1d | 1p*d
16.6 | 4,5# Building the first elevated floor | 16.7 | 7d | 7p*d
16.7 | 4,5# Building construction of structures from the second floor to the twenty-eighth floor | 16.8 | 100d | 100p*d
16.8 | 4,5# Building roof structure construction | 16.9 | 7d | 7p*d
16.9 | 4,5# Building main structure capping | 16.1 | 1d | 1p*d
16.1 | Inspection and acceptance | N/A | 1d | 1p*d
17 | Basement electromechanical installation | 25
17.1 | Construction preparation | 17.2 | 2d | 2p*d
17.2 | Electrical and plumbing works | 17.3,17.4,17.5 | 14d | 14p*d
17.3 | Wall and ceiling decoration | 17.6 | 21d | 21p*d
17.4 | Fitting out works | 17.7 | 14d | 14p*d
17.5 | Clean up | 17.7 | 5d | 5p*d
17.6 | Floor works | 17.7 | 14d | 14p*d
17.7 | Inspection | N/A | 2d | 2p*d
18 | 1,2# Building electromechanical installation | 25
18.1 | Construction preparation | 18.2,18.8 | 2d | 2p*d
18.2 | 1# Building electrical and plumbing works | 18.3,18.4,18.5,18.6 | 25d | 25p*d
18.3 | 1# Building wall and ceiling decoration | 18.7 | 30d | 30p*d
18.4 | 1# Building fitting out works | 18.14 | 25d | 25p*d
18.5 | 1# Building clean up | 18.14 | 5d | 5p*d
18.6 | 1# Building elevator installation | 18.14 | 25d | 25p*d
18.7 | 1# Building floor works | 18.14 | 25d | 25p*d
18.8 | 2# Building electrical and plumbing works | 18.9,18.10,18.11,18.12 | 25d | 25p*d
18.9 | 2# Building wall and ceiling decoration | 18.13 | 30d | 30p*d
18.1 | 2# Building fitting out works | 18.14 | 25d | 25p*d
18.11 | 2# Building clean up | 18.14 | 5d | 5p*d
18.12 | 2# Building elevator installation | 18.14 | 25d | 25p*d
18.13 | 2# Building floor works | 18.14 | 25d | 25p*d
18.14 | Inspection and acceptance | N/A | 2d | 2p*d
19 | 1, 2# Roofing works | 25
19.1 | Construction preparation | 19.2,19.3,19.4,19.5 | 2d | 2p*d
19.2 | 1# Building roofing installation | 19.6 | 14d | 14p*d
19.3 | 1# Building roofing decoration | 19.6 | 6d | 6p*d
19.4 | 2# Building roofing installation | 19.6 | 14d | 14p*d
19.5 | 2# Building roofing decoration | 19.6 | 6d | 6p*d
19.6 | Inspection and acceptance | N/A | 2d | 2p*d
20 | 3,4,5# building electromechanical decoration | 25
20.1 | Construction preparation | 20.2,20.8 | 2d | 2p*d
20.2 | 3# Building electrical and plumbing works | 20.3,20.4,20.5,20.6 | 24d | 24p*d
20.3 | 3# Building wall and ceiling decoration | 20.7 | 30d | 30p*d
20.4 | 3# Building fitting out works | 20.14 | 24d | 24p*d
20.5 | 3# Building clean up | 20.14 | 5d | 5p*d
20.6 | 3# Building elevator installation | 20.14 | 30d | 30p*d
20.7 | 3# Building floor works | 20.14 | 24d | 24p*d
20.8 | 4,5# Building electrical and plumbing works | 20.9,20.10,20.11,20.12 | 24d | 24p*d
20.9 | 4,5# Building wall and ceiling decoration | 20.13 | 30d | 30p*d
20.1 | 4,5# Building fitting out works | 20.14 | 24d | 24p*d
20.11 | 4,5# Building clean up | 20.14 | 5d | 5p*d
20.12 | 4,5# Building elevator installation | 20.14 | 24d | 24p*d
20.13 | 4,5# Building floor works | 20.14 | 24d | 24p*d
20.14 | Inspection and acceptance | N/A | 2d | 2p*d
21 | 3,4,5# Roofing works | 25
21.1 | Construction preparation | 21.2,21.3,21.4,21.5 | 1d | 1p*d
21.2 | 3# Building roofing installation | 21.6 | 12d | 12p*d
21.3 | 3# Building roofing decoration | 21.6 | 5d | 5p*d
21.4 | 4,5# Building roofing installation | 21.6 | 12d | 12p*d
21.5 | 4,5# Building roofing decoration | 21.6 | 5d | 5p*d
21.6 | Inspection and acceptance | N/A | 1d | 1p*d
22 | Outdoor works | 25
22.1 | Construction preparation | 22.2,22.3 | 1d | 1p*d
22.2 | Municipal water and electricity | 22.4 | 5d | 5p*d
22.3 | Road structure | 22.5 | 21d | 21p*d
22.4 | Greening works | 22.6 | 5d | 5p*d
22.5 | Pavement works | 22.6 | 14d | 14p*d
22.6 | Inspection and acceptance | N/A | 1d | 1p*d
23 | 1, 2# Construction equipment demolition | 25
23.1 | Construction preparation | 23.2,23.3,23.4,23.5 | 1d | 1p*d
23.2 | 1# Building scaffolding demolition | 23.6 | 10d | 10p*d
23.3 | 1# Building tower crane demolition | 23.7 | 10d | 10p*d
23.4 | 1# Building construction elevator demolition | 23.8 | 10d | 10p*d
23.5 | Building facade works | 23.9 | 4d | 4p*d
23.6 | 2# Building scaffolding demolition | 23.9 | 10d | 10p*d
23.7 | 2# Building tower crane demolition | 23.9 | 10d | 10p*d
23.8 | 2# Building construction elevator demolition | 23.9 | 10d | 10p*d
23.9 | Inspection and acceptance | N/A | 1d | 1p*d
24 | 3,4,5# Construction equipment demolition | 25
24.1 | Construction preparation | 24.2,24.3,24.4,24.5 | 1d | 1p*d
24.2 | 3# Building scaffolding demolition | 24.6 | 10d | 10p*d
24.3 | 3# Building tower crane demolition | 24.7 | 10d | 10p*d
24.4 | 3# Building construction elevator demolition | 24.8 | 10d | 10p*d
24.5 | Building facade works | 24.9 | 4d | 4p*d
24.6 | 4,5# Building scaffolding demolition | 24.9 | 10d | 10p*d
24.7 | 4,5# Building tower crane demolition | 24.9 | 10d | 10p*d
24.8 | 4,5# Building construction elevator demolition | 24.9 | 10d | 10p*d
24.9 | Inspection and acceptance | N/A | 1d | 1p*d
25 | Project inspection and acceptance | 26
25.1 | Linkage test | 25.3 | 4d | 4p*d
25.2 | Fire inspection and acceptance | 25.3 | 4d | 4p*d
25.3 | Completion initial inspection and acceptance | 25.4 | 4d | 4p*d
25.4 | Completion final inspection and acceptance | N/A | 4d | 4p*d
26 | Dummy work package | N/A | 0 | 0

## STOA heuristics
W
10 | ([[0], [16], [23], [28], [29], [43], [46], [64], [65], [69], [132], [144], [155], [168], [178], [186], [193], [202], [203], [212], [214], [219], [220], [221], [227], [233], [234], [239], [241], [247], [254], [266], [274], [275], [283], [288], [161, 162, 163, 164, 165, 166, 167, 187], [188, 189, 190, 191, 192, 213], [198, 199, 200, 201], [133, 134, 135, 136, 137, 138], [180, 181, 182], [204, 205, 206, 207], [183, 184, 185], [208, 209, 210, 211], [262, 264], [194, 195, 196, 197], [145, 147, 156, 158], [139, 140, 141, 142, 143, 150, 151, 152, 153, 154], [157, 22, 146], [24, 26, 25, 27], [248, 252, 242, 246], [57, 56, 55, 148, 149, 32, 31, 30, 62, 179, 58, 59, 60, 61, 35, 36, 33, 34], [229, 231, 223, 225, 224, 230], [82, 80, 85, 83, 88, 86, 91, 89, 94, 92, 97, 95, 98, 100, 101, 102, 103, 104, 105, 106, 107, 118, 115, 112, 109, 44, 45, 47, 48, 217, 49, 216, 108, 111, 114, 117], [67, 68, 77, 74, 71, 70, 79, 76, 73, 72, 75, 78, 81, 84, 87, 90, 93, 96, 99], [222, 226, 228, 232], [259, 244, 250, 243, 245, 249, 251], [63, 66, 42, 41, 38, 40, 37, 39], [265, 253, 286, 287, 284, 285], [18, 17, 19, 20, 21], [15, 3, 4, 5, 14, 9, 7, 6, 8, 10, 11, 12, 13, 1, 2], [123, 124, 128, 129, 125, 126, 130, 127, 131], [159, 160], [177, 169, 170, 171, 172, 173, 174, 175, 176], [240, 260], [268, 272, 269, 273, 267, 271, 270, 238, 236, 235, 237], [277, 281, 278, 282, 276, 280, 279, 258, 256, 261, 263, 255, 257], [215, 218, 110, 113, 116, 119, 122, 121, 120, 52, 53, 54, 50, 51]], 324, 16361.304285391589)
20 | ([[0], [16], [23], [28], [29], [43], [46], [64], [65], [69], [132], [144], [155], [168], [178], [186], [193], [202], [203], [212], [214], [219], [220], [221], [227], [233], [234], [239], [241], [247], [254], [266], [274], [275], [283], [288], [161, 162, 163, 164, 165, 166, 167, 187], [188, 189, 190, 191, 192, 213], [133, 134, 135, 136, 137, 138], [180, 181, 182], [183, 184, 185], [145, 147, 156, 158], [139, 140, 141, 142, 143, 150, 151, 152, 153, 154], [157, 22, 146], [24, 26, 25, 27], [57, 56, 55, 148, 149, 32, 31, 30, 62, 179, 58, 59, 60, 61, 35, 36, 33, 34], [229, 231, 223, 225, 224, 230], [222, 226, 228, 232], [259, 244, 250, 243, 245, 249, 251], [63, 66, 42, 41, 38, 40, 37, 39], [265, 253, 286, 287, 284, 285], [18, 17, 19, 20, 21], [15, 3, 4, 5, 14, 9, 7, 6, 8, 10, 11, 12, 13, 1, 2], [123, 124, 128, 129, 125, 126, 130, 127, 131], [159, 160], [177, 169, 170, 171, 172, 173, 174, 175, 176], [240, 260], [268, 272, 269, 273, 267, 271, 270, 238, 236, 235, 237], [277, 281, 278, 282, 276, 280, 279, 258, 256, 261, 263, 255, 257], [67, 68, 77, 74, 71, 70, 79, 76, 73, 72, 75, 78, 81, 84, 87, 90, 93, 96, 99, 82, 80, 85, 83, 88, 86, 91, 89, 94, 92, 97, 95, 98, 100, 101, 102, 103, 104, 105, 106, 107, 118, 115, 112, 109, 44, 45, 47, 48, 217, 49, 216, 108, 111, 114, 117, 215, 218, 110, 113, 116, 119, 122, 121, 120, 52, 53, 54, 50, 51], [262, 264, 248, 252, 242, 246], [198, 199, 200, 201, 194, 195, 196, 197], [204, 205, 206, 207, 208, 209, 210, 211]], 324, 17004.401719214125)
30 | ([[0], [16], [23], [28], [29], [43], [46], [64], [65], [69], [132], [144], [155], [168], [178], [186], [193], [202], [203], [212], [214], [219], [220], [221], [227], [233], [234], [239], [241], [247], [254], [266], [274], [275], [283], [288], [161, 162, 163, 164, 165, 166, 167, 187], [188, 189, 190, 191, 192, 213], [133, 134, 135, 136, 137, 138], [180, 181, 182], [183, 184, 185], [145, 147, 156, 158], [139, 140, 141, 142, 143, 150, 151, 152, 153, 154], [157, 22, 146], [24, 26, 25, 27], [57, 56, 55, 148, 149, 32, 31, 30, 62, 179, 58, 59, 60, 61, 35, 36, 33, 34], [229, 231, 223, 225, 224, 230], [222, 226, 228, 232], [259, 244, 250, 243, 245, 249, 251], [63, 66, 42, 41, 38, 40, 37, 39], [265, 253, 286, 287, 284, 285], [18, 17, 19, 20, 21], [15, 3, 4, 5, 14, 9, 7, 6, 8, 10, 11, 12, 13, 1, 2], [123, 124, 128, 129, 125, 126, 130, 127, 131], [159, 160], [177, 169, 170, 171, 172, 173, 174, 175, 176], [240, 260], [268, 272, 269, 273, 267, 271, 270, 238, 236, 235, 237], [277, 281, 278, 282, 276, 280, 279, 258, 256, 261, 263, 255, 257], [67, 68, 77, 74, 71, 70, 79, 76, 73, 72, 75, 78, 81, 84, 87, 90, 93, 96, 99, 82, 80, 85, 83, 88, 86, 91, 89, 94, 92, 97, 95, 98, 100, 101, 102, 103, 104, 105, 106, 107, 118, 115, 112, 109, 44, 45, 47, 48, 217, 49, 216, 108, 111, 114, 117, 215, 218, 110, 113, 116, 119, 122, 121, 120, 52, 53, 54, 50, 51], [262, 264, 248, 252, 242, 246], [198, 199, 200, 201, 194, 195, 196, 197], [204, 205, 206, 207, 208, 209, 210, 211]], 324, 17614.401719214125)
40 | ([[0], [16], [23], [28], [29], [43], [46], [64], [65], [69], [132], [144], [155], [168], [178], [186], [193], [202], [203], [212], [214], [219], [220], [221], [227], [233], [234], [239], [241], [247], [254], [266], [274], [275], [283], [288], [161, 162, 163, 164, 165, 166, 167, 187, 188, 189, 190, 191, 192, 213], [133, 134, 135, 136, 137, 138], [180, 181, 182], [183, 184, 185], [145, 147, 156, 158], [139, 140, 141, 142, 143, 150, 151, 152, 153, 154], [157, 22, 146], [24, 26, 25, 27], [148, 57, 56, 55, 149, 32, 31, 30, 62, 179, 58, 59, 60, 61, 35, 36, 33, 34], [229, 231, 223, 225, 224, 230], [222, 226, 228, 232], [259, 244, 250, 243, 249, 245, 251], [63, 66, 42, 41, 38, 40, 37, 39], [265, 253, 286, 287, 284, 285], [18, 17, 19, 20, 21], [15, 3, 4, 5, 14, 9, 7, 6, 8, 10, 11, 12, 13, 1, 2], [123, 124, 128, 129, 125, 126, 130, 127, 131], [159, 160], [177, 169, 170, 171, 172, 173, 174, 175, 176], [240, 260], [268, 272, 269, 273, 267, 271, 270, 238, 236, 235, 237], [277, 281, 278, 282, 276, 280, 279, 258, 256, 261, 263, 255, 257], [67, 68, 77, 74, 71, 70, 79, 76, 73, 72, 75, 78, 81, 84, 87, 90, 93, 96, 99, 82, 80, 85, 83, 88, 86, 91, 89, 94, 92, 97, 95, 98, 100, 101, 102, 103, 104, 105, 106, 107, 118, 115, 112, 109, 44, 45, 47, 48, 217, 49, 216, 108, 111, 114, 117, 215, 218, 110, 113, 116, 119, 122, 121, 120, 52, 53, 54, 50, 51], [262, 264, 248, 252, 242, 246], [198, 199, 200, 201, 194, 195, 196, 197], [204, 205, 206, 207, 208, 209, 210, 211]], 324, 18214.500493856976)
50 | ([[0], [16], [23], [28], [29], [43], [46], [64], [65], [69], [132], [144], [155], [168], [178], [193], [202], [203], [212], [214], [219], [221], [227], [233], [234], [239], [241], [247], [254], [266], [274], [275], [283], [288], [161, 162, 163, 164, 165, 166, 167, 187, 188, 189, 190, 191, 192, 213], [133, 134, 135, 136, 137, 138], [222, 226, 228, 232], [259, 244, 250, 243, 249, 245, 251], [265, 253, 286, 287, 284, 285], [123, 124, 128, 129, 125, 126, 130, 127, 131], [177, 169, 170, 171, 172, 173, 174, 175, 176], [240, 260], [67, 68, 77, 74, 71, 70, 79, 76, 73, 72, 75, 78, 81, 84, 87, 90, 93, 96, 99, 82, 80, 85, 83, 88, 86, 91, 89, 94, 92, 97, 95, 98, 100, 101, 102, 103, 104, 105, 106, 107, 118, 115, 112, 109, 44, 45, 47, 48, 217, 49, 216, 108, 111, 114, 117, 215, 218, 110, 113, 116, 119, 122, 121, 120, 52, 53, 54, 50, 51], [262, 264, 248, 252, 242, 246], [198, 199, 200, 201, 194, 195, 196, 197], [204, 205, 206, 207, 208, 209, 210, 211], [186, 183, 184, 185, 148, 57, 56, 55, 149, 32, 31, 30, 62, 179, 58, 59, 60, 61, 35, 36, 33, 34, 180, 181, 182, 63, 66, 42, 41, 38, 40, 37, 39], [229, 231, 223, 225, 224, 230, 277, 281, 278, 282, 276, 280, 279, 258, 256, 261, 263, 255, 257], [220, 268, 272, 269, 273, 267, 271, 270, 238, 236, 235, 237], [24, 26, 25, 27, 159, 160], [18, 17, 19, 20, 21, 145, 147, 156, 158, 157, 22, 146], [139, 140, 141, 142, 143, 150, 151, 152, 153, 154, 15, 3, 4, 5, 14, 9, 7, 6, 8, 10, 11, 12, 13, 1, 2]], 330, 18537.620429095543)
60 | ([[0], [16], [23], [28], [29], [43], [46], [64], [65], [69], [132], [144], [155], [168], [178], [193], [202], [203], [212], [214], [219], [221], [227], [233], [234], [239], [241], [247], [254], [266], [274], [275], [283], [288], [161, 162, 163, 164, 165, 166, 167, 187, 188, 189, 190, 191, 192, 213], [133, 134, 135, 136, 137, 138], [222, 226, 228, 232], [259, 244, 250, 243, 249, 245, 251], [265, 253, 286, 287, 284, 285], [123, 124, 128, 129, 125, 126, 130, 127, 131], [177, 169, 170, 171, 172, 173, 174, 175, 176], [240, 260], [67, 68, 77, 74, 71, 70, 79, 76, 73, 72, 75, 78, 81, 84, 87, 90, 93, 96, 99, 82, 80, 85, 83, 88, 86, 91, 89, 94, 92, 97, 95, 98, 100, 101, 102, 103, 104, 105, 106, 107, 118, 115, 112, 109, 44, 45, 47, 48, 217, 49, 216, 108, 111, 114, 117, 215, 218, 110, 113, 116, 119, 122, 121, 120, 52, 53, 54, 50, 51], [262, 264, 248, 252, 242, 246], [198, 199, 200, 201, 194, 195, 196, 197], [204, 205, 206, 207, 208, 209, 210, 211], [186, 183, 184, 185, 148, 57, 56, 55, 149, 32, 31, 30, 62, 179, 58, 59, 60, 61, 35, 36, 33, 34, 180, 181, 182, 63, 66, 42, 41, 38, 40, 37, 39], [229, 231, 223, 225, 224, 230, 277, 281, 278, 282, 276, 280, 279, 258, 256, 261, 263, 255, 257], [220, 268, 272, 269, 273, 267, 271, 270, 238, 236, 235, 237], [24, 26, 25, 27, 159, 160], [18, 17, 19, 20, 21, 145, 147, 156, 158, 157, 22, 146], [139, 140, 141, 142, 143, 150, 151, 152, 153, 154, 15, 3, 4, 5, 14, 9, 7, 6, 8, 10, 11, 12, 13, 1, 2]], 330, 19037.620429095543)
70 | ([[0], [16], [23], [28], [29], [43], [46], [64], [65], [69], [132], [144], [155], [168], [178], [193], [202], [203], [212], [214], [219], [221], [227], [233], [234], [239], [241], [247], [254], [266], [274], [275], [283], [288], [161, 162, 163, 164, 165, 166, 167, 187, 188, 189, 190, 191, 192, 213], [133, 134, 135, 136, 137, 138], [222, 226, 228, 232], [265, 253, 286, 287, 284, 285], [123, 124, 128, 129, 125, 126, 130, 127, 131], [177, 169, 170, 171, 172, 173, 174, 175, 176], [240, 260], [67, 68, 77, 74, 71, 70, 79, 76, 73, 72, 75, 78, 81, 84, 87, 90, 93, 96, 99, 82, 80, 85, 83, 88, 86, 91, 89, 94, 92, 97, 95, 98, 100, 101, 102, 103, 104, 105, 106, 107, 118, 115, 112, 109, 44, 45, 47, 48, 217, 49, 216, 108, 111, 114, 117, 215, 218, 110, 113, 116, 119, 122, 121, 120, 52, 53, 54, 50, 51], [198, 199, 200, 201, 194, 195, 196, 197], [204, 205, 206, 207, 208, 209, 210, 211], [186, 183, 184, 185, 148, 57, 56, 55, 149, 32, 31, 30, 62, 179, 58, 59, 60, 61, 35, 36, 33, 34, 180, 181, 182, 63, 66, 42, 41, 38, 40, 37, 39], [229, 231, 223, 225, 224, 230, 277, 281, 278, 282, 276, 280, 279, 258, 256, 261, 263, 255, 257], [220, 268, 272, 269, 273, 267, 271, 270, 238, 236, 235, 237], [24, 26, 25, 27, 159, 160], [18, 17, 19, 20, 21, 145, 147, 156, 158, 157, 22, 146], [139, 140, 141, 142, 143, 150, 151, 152, 153, 154, 15, 3, 4, 5, 14, 9, 7, 6, 8, 10, 11, 12, 13, 1, 2], [259, 244, 250, 243, 249, 245, 251, 262, 264, 248, 252, 242, 246]], 331, 19529.72351966346)
80 | ([[0], [16], [23], [28], [29], [43], [46], [64], [65], [69], [132], [144], [155], [168], [178], [193], [202], [203], [212], [214], [219], [221], [227], [233], [234], [239], [241], [247], [254], [266], [274], [275], [283], [288], [161, 162, 163, 164, 165, 166, 167, 187, 188, 189, 190, 191, 192, 213], [133, 134, 135, 136, 137, 138], [222, 226, 228, 232], [265, 253, 286, 287, 284, 285], [123, 124, 128, 129, 125, 126, 130, 127, 131], [177, 169, 170, 171, 172, 173, 174, 175, 176], [240, 260], [67, 68, 77, 74, 71, 70, 79, 76, 73, 72, 75, 78, 81, 84, 87, 90, 93, 96, 99, 82, 80, 85, 83, 88, 86, 91, 89, 94, 92, 97, 95, 98, 100, 101, 102, 103, 104, 105, 106, 107, 118, 115, 112, 109, 44, 45, 47, 48, 217, 49, 216, 108, 111, 114, 117, 215, 218, 110, 113, 116, 119, 122, 121, 120, 52, 53, 54, 50, 51], [198, 199, 200, 201, 194, 195, 196, 197], [204, 205, 206, 207, 208, 209, 210, 211], [186, 183, 184, 185, 148, 57, 56, 55, 149, 32, 31, 30, 62, 179, 58, 59, 60, 61, 35, 36, 33, 34, 180, 181, 182, 63, 66, 42, 41, 38, 40, 37, 39], [229, 231, 223, 225, 224, 230, 277, 281, 278, 282, 276, 280, 279, 258, 256, 261, 263, 255, 257], [220, 268, 272, 269, 273, 267, 271, 270, 238, 236, 235, 237], [24, 26, 25, 27, 159, 160], [18, 17, 19, 20, 21, 145, 147, 156, 158, 157, 22, 146], [139, 140, 141, 142, 143, 150, 151, 152, 153, 154, 15, 3, 4, 5, 14, 9, 7, 6, 8, 10, 11, 12, 13, 1, 2], [259, 244, 250, 243, 249, 245, 251, 262, 264, 248, 252, 242, 246]], 331, 20019.72351966346)
90 | ([[0], [16], [23], [28], [29], [43], [46], [64], [65], [69], [132], [144], [155], [168], [178], [193], [202], [203], [212], [214], [219], [221], [227], [233], [234], [239], [241], [247], [254], [266], [274], [275], [283], [288], [161, 162, 163, 164, 165, 166, 167, 187, 188, 189, 190, 191, 192, 213], [133, 134, 135, 136, 137, 138], [265, 253, 286, 287, 284, 285], [177, 169, 170, 171, 172, 173, 174, 175, 176], [240, 260], [67, 68, 77, 74, 71, 70, 79, 76, 73, 72, 75, 78, 81, 84, 87, 90, 93, 96, 99, 82, 80, 85, 83, 88, 86, 91, 89, 94, 92, 97, 95, 98, 100, 101, 102, 103, 104, 105, 106, 107, 118, 115, 112, 109, 44, 45, 47, 48, 217, 49, 216, 108, 111, 114, 117, 215, 218, 110, 113, 116, 119, 122, 121, 120, 52, 53, 54, 50, 51], [198, 199, 200, 201, 194, 195, 196, 197], [204, 205, 206, 207, 208, 209, 210, 211], [186, 183, 184, 185, 148, 57, 56, 55, 149, 32, 31, 30, 62, 179, 58, 59, 60, 61, 35, 36, 33, 34, 180, 181, 182, 63, 66, 42, 41, 38, 40, 37, 39], [220, 268, 272, 269, 273, 267, 271, 270, 238, 236, 235, 237], [259, 244, 250, 243, 245, 249, 251, 229, 231, 223, 225, 224, 230, 277, 281, 278, 282, 276, 280, 279, 258, 256, 261, 263, 255, 257], [222, 226, 228, 232, 262, 264, 248, 252, 242, 246], [24, 26, 25, 27, 159, 160], [18, 17, 19, 20, 21, 145, 147, 156, 158, 157, 22, 146], [139, 140, 141, 142, 143, 150, 151, 152, 153, 154, 15, 3, 4, 5, 14, 9, 7, 6, 8, 10, 11, 12, 13, 1, 2, 123, 124, 128, 129, 125, 126, 130, 127, 131]], 333, 20571.747702948902)
100 | ([[0], [16], [23], [28], [29], [43], [46], [64], [65], [69], [132], [144], [155], [168], [178], [193], [202], [203], [212], [214], [219], [221], [227], [233], [234], [239], [241], [247], [254], [266], [274], [275], [283], [288], [161, 162, 163, 164, 165, 166, 167, 187, 188, 189, 190, 191, 192, 213], [133, 134, 135, 136, 137, 138], [265, 253, 286, 287, 284, 285], [177, 169, 170, 171, 172, 173, 174, 175, 176], [240, 260], [67, 68, 77, 74, 71, 70, 79, 76, 73, 72, 75, 78, 81, 84, 87, 90, 93, 96, 99, 82, 80, 85, 83, 88, 86, 91, 89, 94, 92, 97, 95, 98, 100, 101, 102, 103, 104, 105, 106, 107, 118, 115, 112, 109, 44, 45, 47, 48, 217, 49, 216, 108, 111, 114, 117, 215, 218, 110, 113, 116, 119, 122, 121, 120, 52, 53, 54, 50, 51], [198, 199, 200, 201, 194, 195, 196, 197], [204, 205, 206, 207, 208, 209, 210, 211], [186, 183, 184, 185, 148, 57, 56, 55, 149, 32, 31, 30, 62, 179, 58, 59, 60, 61, 35, 36, 33, 34, 180, 181, 182, 63, 66, 42, 41, 38, 40, 37, 39], [220, 268, 272, 269, 273, 267, 271, 270, 238, 236, 235, 237], [259, 244, 250, 243, 245, 249, 251, 229, 231, 223, 225, 224, 230, 277, 281, 278, 282, 276, 280, 279, 258, 256, 261, 263, 255, 257], [222, 226, 228, 232, 262, 264, 248, 252, 242, 246], [24, 26, 25, 27, 159, 160], [18, 17, 19, 20, 21, 145, 147, 156, 158, 157, 22, 146], [139, 140, 141, 142, 143, 150, 151, 152, 153, 154, 15, 3, 4, 5, 14, 9, 7, 6, 8, 10, 11, 12, 13, 1, 2, 123, 124, 128, 129, 125, 126, 130, 127, 131]], 333, 21041.747702948902)

## TLGA
W
10 | (17197.56800302309,array([[0,2,132,139,161,133,1,3,162,4,123,128,5,140,124,125,150,126,151,134,152,130,129,12,141,135,131,163,6,127,142,136,164,165,143,153,154,155,156,158,8,10,166,167,7,14,137,138,13,15,9,144,157,11,187,188,189,190,191,168,173,169,170,171,174,175,176,172,177,147,146,145,16,17,18,148,159,160,178,183,179,149,19,20,184,180,181,182,185,186,21,22,193,198,194,199,195,196,197,200,201,202,234,238,235,23,192,213,214,217,215,216,218,203,25,204,24,208,27,219,26,266,209,205,206,207,28,57,56,55,269,267,220,268,227,270,228,229,230,232,272,271,231,236,221,225,222,273,237,223,224,226,274,233,239,210,211,29,31,32,30,58,59,33,34,35,36,60,37,61,38,40,62,39,41,63,212,260,275,240,247,66,69,42,254,276,279,256,280,257,258,278,255,277,262,264,241,261,282,281,244,243,263,43,44,64,72,67,70,73,46,242,245,248,249,251,250,252,265,259,246,283,253,285,284,286,287,65,47,49,50,45,52,53,87,90,77,80,93,85,83,86,88,96,91,89,92,94,95,97,98,99,102,105,100,103,106,108,101,109,111,114,104,117,107,120,110,112,113,115,118,121,116,119,122,288],[1,0,1,1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,1,0,0,0,0,0,0,1,1,1,0,0,0,0,0,0,1,0,0,1,0,1,1,0,1,0,1,0,0,1,1,0,1,0,0,1,0,0,0,0,0,0,1,1,0,0,1,0,1,1,0,1,0,1,0,0,1,0,0,0,0,0,1,1,0,0,0,0,0,0,0,1,0,1,0,1,1,0,1,1,0,1,0,1,1,0,0,0,0,1,1,1,1,1,0,0,1,1,0,0,1,0,0,0,1,1,1,0,0,1,0,0,0,0,1,1,1,0,0,0,0,0,1,0,0,1,0,1,1,0,0,1,0,0,0,1,0,0,0,1,0,1,0,0,0,0,1,1,1,1,1,1,1,1,1,1,0,1,0,0,0,1,0,0,0,0,1,1,0,0,0,0,0,1,1,1,1,0,0,0,1,1,0,0,0,0,1,0,0,0,0,1,1,0,0,0,0,1,1,0,1,0,0,0,1,0,0,1,0,0,1,0,0,0,0,0,0,0,0,0,0,1,0,0,0,0,0,0,1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,1,0,0,0,0,0,0,1,0,0,0,0,0,0,1]])
20 | 18480.142169861203_[[ 0 2 161 132 150 139 140 151 141 1 133 3 142 4 5 6 134 123 124 128 130 129 126 125 127 162 131 163 168 173 174 135 175 136 169 137 138 152 12 164 13 143 165 153 8 14 7 15 9 166 167 10 154 11 144 145 146 147 148 149 155 157 158 156 159 160 178 187 179 183 16 18 19 17 20 21 22 176 188 170 171 189 172 177 180 184 181 185 182 190 186 23 24 25 27 26 191 192 213 214 217 203 215 218 216 219 208 204 205 209 210 211 206 207 212 275 240 279 276 241 242 247 277 248 193 194 198 199 195 196 200 201 197 202 266 270 220 234 238 237 267 227 268 228 230 244 280 249 246 231 232 272 229 28 56 57 29 32 30 55 31 58 33 34 59 60 61 35 62 36 254 255 260 221 236 223 271 222 235 262 261 258 257 269 251 224 256 225 226 233 239 278 282 245 243 273 250 281 264 263 259 252 274 38 40 37 39 41 42 63 66 64 67 283 265 253 284 285 286 287 69 65 43 46 44 47 45 48 72 49 50 70 73 52 51 75 76 78 53 68 71 74 77 81 84 54 79 80 82 87 90 93 96 99 85 88 102 105 91 83 94 97 108 86 89 111 100 103 106 92 95 109 112 98 101 104 107 114 115 117 120 118 121 110 113 116 119 122 288] [ 1 0 0 1 1 0 0 0 0 0 0 0 0 0 0 0 0 1 0 0 0 0 0 0 0 0 0 0 1 1 0 0 0 0 0 0 0 1 0 0 1 0 1 0 0 1 0 0 0 0 0 1 0 0 1 1 0 1 0 0 1 1 0 0 0 0 1 1 1 0 1 1 0 0 0 0 0 1 0 0 0 1 0 0 1 0 1 0 0 0 0 1 1 0 0 0 1 0 0 1 1 1 1 0 0 1 1 1 0 0 1 0 1 0 1 0 1 1 0 1 1 1 1 0 1 1 1 0 0 0 0 0 0 1 0 1 0 1 1 1 0 1 1 1 0 0 1 0 0 0 1 0 0 1 1 0 1 1 0 0 0 1 0 0 1 0 0 0 0 0 1 1 0 1 1 0 0 0 1 0 1 0 0 1 0 0 1 0 0 1 0 1 0 0 1 0 1 0 0 0 1 0 1 1 0 0 0 1 0 0 0 1 1 1 1 0 0 0 0 0 1 0 0 0 1 0 0 1 0 0 0 0 0 1 0 0 1 0 0 1 0 1 0 0 1 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 1 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 1]]
30 | 19482.1868764752_[[ 0 123 161 132 2 150 139 133 151 162 1 3 128 130 134 124 125 126 129 131 4 5 163 135 127 12 13 136 140 164 6 141 142 165 7 8 152 153 154 155 158 156 157 159 160 178 179 183 168 169 143 144 9 10 173 14 166 167 187 11 15 188 146 145 189 190 148 16 18 147 170 174 175 171 137 176 184 17 19 138 149 172 177 193 198 194 199 195 196 197 200 201 202 266 185 180 181 191 192 182 186 20 213 21 214 22 217 215 216 218 23 24 25 27 26 219 28 57 55 203 204 208 234 209 205 29 56 31 220 221 206 210 30 32 58 211 207 59 212 60 61 240 260 241 261 237 236 227 235 228 270 268 269 273 262 247 263 267 225 222 238 272 229 271 230 224 231 223 239 33 34 35 62 36 38 37 39 40 41 63 42 66 64 232 226 275 254 256 276 277 274 233 278 279 255 281 245 242 244 258 257 280 251 282 249 248 250 43 246 243 252 264 69 44 46 67 72 70 75 45 78 283 259 253 265 284 285 286 287 65 49 50 47 48 51 52 53 54 68 81 73 71 74 76 84 87 77 79 82 85 90 80 83 88 93 96 86 91 94 99 97 100 89 92 95 102 105 108 98 111 103 114 117 120 101 104 106 107 109 112 110 115 118 113 121 116 119 122 288] [ 1 0 0 1 1 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 1 1 0 0 0 0 1 1 0 1 1 0 1 1 0 0 0 0 0 0 1 0 0 0 1 0 0 0 1 1 1 0 0 0 0 0 1 0 1 0 0 0 1 0 1 1 0 0 0 0 0 0 0 1 0 1 1 0 0 0 1 0 1 0 0 1 1 0 0 0 0 1 1 0 0 0 1 0 1 0 1 1 0 1 1 0 1 1 0 0 1 1 0 0 0 1 0 0 0 1 1 0 0 0 1 1 0 0 1 1 1 0 1 0 0 0 1 1 1 0 0 1 0 0 1 0 0 0 0 1 1 0 0 1 0 0 0 0 1 0 0 0 0 1 1 0 1 0 1 0 0 1 0 1 0 0 1 0 0 1 0 0 0 1 0 1 0 0 1 1 0 0 0 1 1 1 1 1 0 0 0 0 1 1 0 1 0 0 1 0 1 1 0 0 0 0 1 0 0 1 0 0 1 0 0 0 0 0 1 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 1]]
40 | 19889.105657212138_[[ 0 132 123 133 150 1 151 139 2 161 162 134 135 152 3 163 140 128 4 141 164 165 5 130 142 129 153 154 131 6 124 143 12 136 125 126 13 14 166 7 8 127 167 144 146 168 145 187 169 188 147 170 15 173 9 174 137 175 138 171 155 156 157 158 159 160 10 11 178 189 190 148 149 183 179 16 18 17 19 20 21 22 176 172 177 184 185 193 194 198 199 195 200 196 201 197 202 191 192 213 23 25 24 214 216 217 215 218 219 180 181 26 27 182 186 203 204 208 28 29 32 57 30 55 31 33 34 56 58 266 234 220 227 59 60 61 62 35 36 37 38 40 39 41 63 238 237 268 66 64 272 267 67 235 269 69 205 209 210 211 206 207 212 240 260 275 278 273 221 225 229 247 262 230 231 270 223 271 236 224 222 226 228 232 239 274 233 42 254 258 279 257 277 255 241 242 249 248 261 282 256 245 243 250 276 280 43 281 264 263 265 251 252 259 246 244 65 72 75 68 283 253 284 285 286 287 44 45 46 49 47 48 52 50 70 51 53 73 78 54 71 81 76 79 82 74 84 87 77 90 93 96 99 102 80 85 83 86 88 91 105 108 111 89 94 97 92 100 95 98 103 106 114 101 109 104 107 112 110 113 115 117 120 118 121 116 119 122 288] [ 1 0 1 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 1 0 1 0 1 1 1 1 1 0 0 0 0 0 1 0 0 0 1 0 0 1 1 0 0 0 1 0 0 1 1 0 0 0 0 0 1 1 0 0 0 0 0 0 0 0 1 0 1 1 0 1 0 0 0 0 0 1 1 0 0 1 1 0 1 1 0 0 0 1 1 0 1 0 0 0 1 1 0 1 0 1 0 1 0 0 0 0 0 0 1 0 1 1 1 0 0 0 0 0 0 0 1 0 0 0 1 0 0 0 1 1 0 1 0 0 1 1 0 0 0 0 0 1 1 0 1 1 0 1 1 0 1 1 0 0 0 0 0 0 1 0 0 0 0 1 0 0 1 1 1 0 0 0 0 1 1 0 1 0 0 0 0 1 0 1 0 1 1 0 1 0 0 0 0 0 0 1 1 0 0 1 1 0 0 0 0 0 0 1 1 0 0 1 0 1 0 1 0 0 0 0 0 0 0 1 0 0 0 0 1 0 0 0 0 0 1 0 0 0 0 0 0 1 0 0 0 0 0 0 1 0 0 0 0 0 0 1 0 0 0 0 0 1 0 0 0 0 0 1]]
50 | 20861.04415115834_[[ 0 132 133 123 1 150 124 151 152 161 2 139 125 3 134 140 162 153 163 4 164 141 128 129 130 135 131 126 136 165 166 127 167 154 142 5 12 143 187 144 145 188 168 13 169 155 156 158 157 159 160 6 8 14 173 10 137 138 189 147 146 7 148 149 9 11 15 16 19 18 17 20 190 174 170 171 172 175 176 21 22 191 177 192 178 183 179 184 180 185 181 23 182 25 24 27 26 186 203 204 28 56 213 214 208 193 194 198 195 199 200 196 197 201 202 234 216 215 217 218 57 29 30 31 33 55 266 219 205 209 206 207 210 211 212 254 256 240 260 258 269 270 267 220 227 228 231 232 221 222 229 238 223 268 237 271 273 235 224 236 239 230 226 225 272 233 274 32 58 59 60 34 35 36 38 61 62 37 40 39 41 42 63 43 44 255 275 257 66 278 276 261 277 241 247 281 249 250 279 282 280 259 262 264 69 45 263 243 244 248 251 245 242 72 64 252 265 246 283 253 285 284 286 287 46 49 50 52 51 67 53 54 47 48 65 68 70 75 78 81 73 84 87 90 93 96 71 74 76 77 79 82 80 85 83 99 86 88 102 105 89 91 108 92 94 97 111 100 103 106 109 95 114 117 98 112 120 115 118 101 104 107 110 113 116 121 119 122 288] [ 1 0 1 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 1 0 0 0 0 0 0 0 0 0 0 1 1 0 1 1 0 1 1 0 0 0 0 0 0 0 0 0 1 0 1 0 0 1 0 0 1 0 0 1 1 1 0 0 0 1 0 0 0 0 1 0 0 0 0 0 1 1 0 0 1 0 0 1 1 0 0 0 0 0 1 1 1 1 0 1 1 1 1 0 1 0 1 0 0 0 1 0 1 0 0 0 0 1 1 0 0 0 1 0 1 0 0 0 1 0 1 0 1 0 0 0 1 0 0 0 1 1 0 0 1 1 0 1 0 0 1 0 0 0 1 0 1 1 0 1 0 1 0 1 0 1 0 0 0 0 1 0 0 0 0 1 0 0 0 1 1 0 1 1 0 0 0 1 0 1 0 1 0 0 1 0 0 0 0 0 1 1 0 0 0 0 0 0 0 0 1 1 0 0 1 1 0 0 0 0 1 1 1 0 0 0 0 0 0 0 1 1 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 1 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 1]]
60 | 22969.495566716752_[[ 0 2 161 132 123 124 150 1 139 128 129 162 3 133 126 163 4 164 125 151 140 152 141 142 127 5 6 165 7 153 134 154 143 130 166 155 144 147 8 12 10 157 156 159 167 13 14 146 158 135 160 15 9 187 145 131 178 168 179 148 11 188 136 173 149 16 169 18 174 183 184 189 175 137 138 170 176 171 190 17 191 172 20 180 181 177 192 21 185 19 22 193 182 186 23 25 27 198 194 213 203 195 199 196 200 197 201 214 215 202 266 267 234 237 270 236 238 220 227 229 228 217 268 221 271 232 235 269 224 239 216 273 222 223 226 230 218 272 225 231 274 233 219 24 26 204 208 209 205 210 211 206 207 212 275 240 28 55 56 29 31 57 32 58 59 60 61 62 30 33 34 35 36 38 40 37 39 41 42 260 261 254 256 258 278 276 255 263 277 241 282 242 245 257 243 247 249 251 248 262 279 280 264 265 244 250 252 259 246 281 253 283 63 66 43 46 285 284 286 287 64 65 69 67 70 68 44 72 49 45 47 75 78 73 81 71 74 76 84 77 79 87 50 52 48 51 53 54 82 80 83 90 93 96 85 86 99 88 89 91 92 102 94 97 100 103 105 108 106 109 111 114 95 98 101 117 112 104 115 107 118 120 110 113 121 116 119 122 288] [ 1 0 0 1 1 0 0 0 0 0 0 0 0 1 0 0 1 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 1 0 1 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 1 0 1 0 0 0 0 0 0 1 1 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 1 1 0 1 1 0 1 0 0 1 1 0 0 0 0 0 1 1 1 0 1 1 1 0 0 1 0 1 1 1 0 0 1 1 0 0 1 0 1 1 0 1 0 1 0 0 1 0 0 1 0 0 1 0 0 0 1 0 0 0 0 0 1 0 1 1 1 0 1 1 0 0 1 0 0 0 0 0 1 0 0 0 0 1 0 1 0 0 0 0 1 1 0 1 0 0 0 0 1 1 0 1 0 0 1 1 1 0 1 0 0 1 0 0 0 1 0 0 0 0 1 1 0 1 0 1 0 0 0 1 0 0 1 0 0 1 0 0 0 1 0 1 0 0 0 0 0 0 0 0 1 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 1 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 1 0 0 0 0 0 0 0 0 1]]
70 | 23771.416641502674_[[ 0 132 2 1 3 133 139 123 128 140 161 162 141 4 134 135 129 5 136 124 150 151 130 125 152 163 126 127 131 164 12 153 154 6 8 142 143 165 144 155 157 168 156 146 166 158 147 167 187 173 169 145 174 188 170 189 159 160 178 13 14 10 7 11 9 15 16 18 17 19 20 137 183 179 190 191 148 171 21 149 138 192 213 175 176 184 172 180 22 177 181 23 193 194 198 182 185 186 24 26 25 27 28 29 32 57 214 215 216 199 218 217 219 200 201 203 195 196 197 202 204 208 209 205 206 55 56 31 30 33 34 35 36 207 58 59 60 37 38 266 269 273 234 237 236 267 220 227 230 228 268 238 235 270 221 210 211 212 254 275 260 278 240 40 61 62 39 41 63 42 43 64 46 65 44 277 255 279 262 276 257 241 244 264 282 261 247 222 225 258 248 249 250 245 256 280 224 243 272 281 242 251 252 263 265 271 246 232 223 226 229 231 233 239 274 49 66 52 283 253 259 285 284 286 287 69 67 70 68 47 50 45 72 75 73 78 53 54 71 74 51 48 81 76 84 79 77 80 82 87 83 90 85 88 93 86 89 96 99 91 94 97 102 100 103 105 108 106 92 95 111 98 101 104 114 117 120 109 112 115 107 110 113 118 121 116 119 122 288] [ 1 0 1 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 1 0 0 0 0 0 0 0 0 1 0 1 1 1 0 0 1 0 1 0 0 0 0 0 0 0 0 0 0 1 1 0 0 0 0 0 0 1 1 0 0 0 0 1 0 0 0 0 0 0 0 1 0 0 0 0 0 0 0 0 0 0 1 0 1 0 1 0 0 0 1 0 0 1 0 1 0 1 1 0 0 0 0 1 1 0 1 1 0 0 1 1 0 0 0 1 0 0 1 0 0 0 0 1 0 0 1 0 0 0 1 1 0 1 1 0 0 0 1 1 0 0 0 0 0 1 1 0 1 0 0 1 0 1 0 0 0 0 0 0 0 1 0 0 0 1 1 0 0 0 0 0 1 1 0 0 0 1 1 0 0 0 1 0 0 0 1 0 0 0 1 0 1 0 1 0 0 0 0 0 0 1 0 1 0 0 1 0 0 1 1 0 1 0 0 0 1 1 0 0 0 1 0 0 1 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 1 0 0 0 0 0 0 0 0 0 0 1 0 0 0 1 0 1]]
80 | 25976.417699072477_[[ 0 132 150 2 161 139 151 133 140 152 162 134 1 141 163 3 164 153 135 136 123 137 4 124 125 142 128 165 130 143 5 12 13 6 154 129 14 15 166 8 7 155 144 147 10 146 11 156 157 9 131 16 126 18 138 158 17 127 145 19 159 160 168 20 148 149 167 178 173 21 169 170 171 174 175 183 179 176 187 184 180 188 22 185 181 189 23 172 25 182 24 26 177 190 186 27 28 56 29 31 55 203 30 32 58 57 208 191 192 204 213 193 198 194 195 199 200 201 196 197 202 234 238 237 236 235 239 220 214 221 222 217 215 216 218 219 205 209 210 211 206 207 212 260 261 240 275 276 278 282 263 280 277 254 33 59 60 34 35 266 267 268 271 227 269 272 229 228 273 270 230 223 225 231 232 224 226 274 233 61 36 38 40 37 39 41 42 62 63 66 43 69 46 262 256 258 279 257 255 264 247 251 248 252 250 241 245 249 242 244 246 243 265 281 283 253 259 285 284 286 287 64 65 67 68 70 71 72 44 47 45 75 48 78 49 50 51 52 53 54 81 84 87 90 93 96 73 74 76 77 79 80 99 102 82 85 83 105 88 91 108 111 86 89 94 114 97 92 100 117 95 98 103 120 106 109 112 115 118 101 104 121 107 110 113 116 119 122 288] [ 1 0 1 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 1 0 1 0 0 0 0 0 0 0 1 1 0 0 0 0 0 0 0 0 0 1 1 0 0 0 1 1 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 1 1 0 0 0 0 0 0 0 0 1 1 1 1 0 1 1 0 1 0 0 1 0 0 0 1 1 0 1 0 1 0 0 0 1 0 1 0 0 0 1 1 1 0 1 0 0 1 0 1 1 0 1 0 0 0 1 1 0 0 1 1 1 0 0 0 0 1 1 0 1 0 0 1 1 0 0 1 1 1 0 0 0 1 0 0 0 0 1 0 0 1 0 1 1 0 1 0 1 0 1 0 1 0 1 0 0 1 0 1 0 0 0 0 1 1 0 1 0 1 1 0 0 1 0 1 0 0 1 1 0 1 0 1 0 1 0 1 0 1 0 1 0 0 0 0 1 0 0 0 0 1 0 0 0 0 1 0 0 0 1 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 1 0 0 0 1 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 1]]_12612.983666262
90 | 23591.385828970535_[[ 0 2 123 132 128 1 3 150 133 161 151 129 139 134 135 136 140 124 141 162 163 130 142 126 125 152 153 154 155 131 143 144 4 156 158 157 127 164 165 145 147 146 5 137 12 159 138 160 166 14 6 13 168 7 178 183 169 184 173 148 170 149 179 171 15 185 174 167 8 9 175 187 180 172 176 181 182 177 186 10 11 16 17 19 18 188 20 21 189 190 191 192 193 194 198 195 199 196 197 200 201 202 234 22 213 23 24 25 26 27 203 204 208 205 209 206 210 211 214 207 217 266 215 270 212 220 221 227 228 223 230 222 218 225 224 268 28 29 56 30 31 32 33 57 55 58 59 34 35 216 60 36 38 37 219 40 39 61 62 41 42 63 66 260 261 236 235 237 238 267 271 272 239 269 273 229 231 232 226 274 233 240 254 275 247 241 248 251 258 242 249 245 250 257 243 255 262 256 278 263 264 282 276 265 280 279 277 259 281 246 244 252 43 253 283 284 285 286 287 64 65 69 67 68 72 75 70 44 78 46 47 48 45 49 50 52 53 54 51 81 84 87 71 90 73 93 76 79 96 74 99 77 80 82 83 85 102 88 105 91 86 89 94 97 100 92 95 108 111 114 117 120 103 106 98 101 109 112 104 115 107 110 118 121 113 116 119 122 288] [ 1 0 0 1 1 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 1 1 1 0 1 1 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 1 1 1 1 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 1 0 0 0 1 1 0 1 0 0 0 1 0 0 0 1 1 0 0 0 1 0 0 0 1 0 1 0 1 1 0 0 0 1 1 0 1 0 0 0 0 1 1 0 1 1 0 1 1 1 0 1 0 1 0 0 0 1 0 1 0 1 0 0 1 0 0 0 1 0 0 1 0 0 0 0 0 1 1 0 0 0 0 0 1 0 0 1 0 1 0 0 0 0 0 1 1 0 1 0 0 0 1 0 1 1 0 0 0 1 0 0 0 1 0 0 0 0 0 0 0 0 0 1 0 0 0 0 1 0 0 0 0 0 0 1 1 1 1 0 0 0 1 0 0 1 0 0 0 0 0 0 1 1 0 0 1 0 1 0 0 0 1 0 0 0 0 0 0 0 0 1 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 1 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 1]]_19828.834543786998
100 | 27228.406819781932_[[ 0 132 161 2 139 140 133 1 3 162 163 4 164 5 141 134 150 123 135 165 128 151 124 12 152 14 125 129 126 153 142 130 166 13 154 167 187 15 6 127 131 136 7 155 158 8 157 10 188 11 143 144 168 147 169 173 170 174 9 175 171 172 176 177 137 138 193 194 189 156 159 160 146 145 148 149 178 179 183 184 180 185 181 16 182 18 19 17 20 21 22 23 25 24 27 26 28 57 56 55 58 59 190 191 192 213 214 216 217 215 218 219 198 195 196 199 197 200 201 202 220 234 227 230 221 231 223 235 222 224 225 228 266 269 232 270 226 273 237 236 268 238 272 267 229 271 239 233 274 186 203 204 208 209 210 205 206 29 31 32 30 60 33 34 35 36 38 61 40 211 207 212 240 260 254 256 258 275 255 257 278 279 241 276 262 247 37 39 62 41 42 63 64 65 43 277 264 261 282 248 250 263 281 249 245 244 242 251 243 66 280 44 45 246 252 283 259 265 253 285 284 286 287 46 49 47 48 69 72 67 50 51 52 53 54 68 75 78 81 70 73 71 74 84 76 77 79 82 80 83 87 90 85 86 88 91 89 93 94 92 96 99 102 105 97 100 103 106 108 111 114 109 117 120 112 115 118 95 98 101 104 107 110 113 116 121 119 122 288] [ 1 0 1 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 1 0 1 1 0 0 0 0 0 0 1 0 1 0 0 0 1 0 0 1 0 0 0 1 0 1 1 1 0 0 0 1 0 0 0 1 1 1 0 0 0 0 1 1 0 0 1 0 0 0 1 1 0 0 0 1 1 1 0 0 0 1 0 0 0 1 1 0 0 0 1 1 0 0 0 0 0 0 1 1 1 0 1 1 1 1 0 0 0 0 0 1 1 0 0 0 0 1 0 0 0 0 0 1 0 1 0 0 1 1 1 1 0 0 1 0 1 1 0 1 0 1 0 0 1 0 0 1 0 0 1 1 0 1 1 0 1 1 0 0 0 1 1 0 1 1 0 0 1 0 0 1 0 0 1 0 0 0 0 0 0 0 0 0 0 1 0 1 0 0 1 0 0 0 1 1 1 0 0 0 1 0 1 1 0 0 1 1 0 0 1 0 1 0 1 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 1 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 1]]_14902.628408296001